Institutionalised Partnership in the Field of Promotion of Web Technologies in Sciences and Education (WETSE)

# Title and co-ordinator

Institutionalised Partnership in the Field of Promotion of Web Technologies in Sciences and Education (WETSE)

Co-ordinator :

Dr Daniel Peraya (MER)

TECFA - FPSE University of Geneva

9 route de Drize

CH - 1227 CAROUGE.

# Background and objectives

## Background

To be written by the Russian partners : the first heading of the draft project has to be developed (Needs)

Expected length  : 10-15 lines

The main objective of the project is to organise the Petersburg Consulting and Training Communication Centre for the teaching and training in the field of implementation of new information technologies in sciences and education.

## Objectives

An important part of this sub-chapter has to be written by the Russian partners according to the « Instructions for Preparation of Global Concept », point 2, Annex 1.2., page 3.

The way if feel, two main directions have to be developed :

- the goals of this centre, for instance : to pace? the interest for educational applications of Web technologies, to favour and encourage innovative projects using the Web technologies for education purposes, to teach people, learners, educators, to organise summer schools, and seminars, to gather and disseminate information and documentation, to assess pilot projects, to progressively become a regional « centre of reference » in the field ;

- the links with national or international networks or programs. If such links do exist, our partners have to completely describe the actual context, and situation.

Expected length  : 20 lines

Concerning the Swiss participation, we may add :

The TECFA Unit is involved in numerous either Swiss or European projects and networks. The Russian partners will have the benefit of all the contacts and the existing links in Switzerland and in Europe. For example, Dr D. Peraya is the main contractor of the PRN 42 Project N° 5004-47 955 «  Technology tools and forms of pedagogical communication » that takes place in the context of the Poschiavo Project (Grison). This distance education project is quite important at the moment in Switzerland because of its socio-educational orientation ; it aims to build a model of regional development based on distance education using communication and information technologies. The project involves Swiss Telecoms, the ISPFP (OFIAMT-Lugano), and the participation of Swiss universities (Neufchatel and Geneva). Secondly, TECFA as been partner of the European Humanities project for two years : this project, gathering the most old European universities (Coimbra Group), tried to introduce Web technologies, videoconferences and OFDL (Open and Flexible Distance Learning) to promote virtual mobility into face to face universities. This experience was summarised and will be presented in particular at the EDEN Conference (European Distance Education Network, Budapest, 23-25 June 1997) (Ref. XXX). Tecfa is managing the Swiss educational Web server AGORA and in the frame of the STAF Post graduated Diploma students have developed several educational projects involving primary and secondary schools (Ref. XXX). Finally, Tecfa also participates in the working group « Educational technologies at the university level » (CUS/CUP) and that also an opportunity to contact and meet Swiss institutions and faculties mainly active in the field.

During their stay in Switzerland at Tecfa, the invited members of the Russian Institutes will benefit from all the contacts established by Tecfa, visiting either virtually sites or real pilot-projects.

# Partners

## Tecfa - Educational Technologies Unit of the Faculty of Psychology and Education Sciences, University of Geneva

To be written by D Peraya

Expected length  : ½  - ¾ page

## Vocational Renewal Centre for Management and Computer Technologies

To be written by the partner according to the requirements made in the « Instructions for preparation of Global Concept », point 3, Annex 1.2., page 1.

Expected length  : ½  - ¾ page

## Institute of High Performance Computing Data Bases

To be written by the partner according to the requirements made in the « Instructions for preparation of Global Concept », point 3, Annex 1.2., page 1.

Expected length  : ½  - ¾ page

## Consortium of 15 St Petersburg Universities

To be written by the partner according to the requirements made in the « Instructions for preparation of Global Concept », point 3, Annex 1.2., page 1.

If the Consortium may be considered as a whole, do not give information for each University, but for the Consortium.

Expected length  : ½  - ¾ page

## St Petersburg Union

To be written by the partner according to the requirements made in the « Instructions for preparation of Global Concept », point 3, Annex 1.2., page 1.

Expected length  : ½  - ¾ page

# Content of the IP programme

## Goals

The goals of the project are twofold : to give the Petersburg Centre for the teaching and training in the field of implementation of new technologies in sciences and education the means to be auto-sufficient; on both levels, technical and pedagogical.

That means :

- Technical aspects (Action Line 1) : to contribute to the implementation of the infrastructure and to the organisation of the Centre.

To be written by the CEEC/NIS partners according to the requirements made in the « Instructions for preparation of Global Concept », point 4, Annex 1.2., page 1.

Expected length  : 10 lines maximum

- Information and education aspects  (Action Lines 2 to ) : to teach and train a staff (12 persons, engineers & teachers) able to achieve the goals of the Centre as described above (see the goals of this centre) which will become a « multiplication factor », a « line transmission » for people to be taught and trained in the Centre in St Petersburg. The professional profile will be developed here : a mix of computer sciences and human sciences (psychology, pedagogy, communication sciences). The « multiplication factor » concept will be defined below (Training model, 4.2.). Among the 12 persons to be trained, one engineer will have a particular status and role : he will become the Internet specialist and developer (moo, javascript, vrml, etc.) responsible of all the development aspects in the Centre.

- Pedagogical and methodological aspects are to be developed by D. Peraya. Inputs from the CEEC/NIS partners are welcome.

Expected length  : 10 lines maximum

- Target-public and criteria to be applied for selection are to be defined by the CEEC/NIS partners. This point has to be developed below (4.4.). A brief description is sufficient at this stage.

Expected length  : 10 lines maximum

## Training model

The main idea is to train a limited number of trainers in Geneva which will be, after their stay, tutored and monitored from a distance through the net. Therefore they will learn the pedagogical use of the technologies through their own practice, i. e. at this first moment, practising technologies as distant students. After this stage, they will teach technologies in the Centre, organising training seminars and workshops, and finally reproducing the training system in which they have been taught themselves.

To be developed by D. Peraya. Inputs and comments from the CEEC/NIS partners are welcome.

Expected length  : 20 lines maximum

## Action lines

### Action line 1 : Implementation of technical infrastructure (10.01.97- 01.15.98) and maintenance (01.15.98 – 12.30.98)

To be written by the CEEC/NIS partners according to the requirements made in the « Instructions for preparation of Global Concept », point 4, Annex 1.2., page 1.

For example :

- planing for establishing the infrastructure

- description of the room(s) ;

- machines : number, type, etc... (cf equipment, see below)

- management and organisation ;

- etc.

Expected length  : 20-25 lines maximum

### Action Line 2 : Preparation of training material (10.01.97/01.15.98)

To be written by D Peraya. Design of the seminar : curriculum, aims, contents, modular structure and hybrid organisation (face to face, and at the distance), auto-corrected exercises, setting up the tutoring system through the net, etc.

Inputs and needs are welcome.

Responsible : TECFA

Expected length  : 20-25 lines maximum

### Action Line 3 : training of on Web specialist and developer

- the selected person – an engineer – will attempt the two face to face seminars and an complementary ad-hoc programme in Geneva

- during the two distant follow-up periods he/she will benefit by a specific R & D? programme

- one of his tasks will be the development and implementation of a local moo server for educational purposes and uses (to be set up by the end of the project).

To be developed by D Peraya

Responsible : TECFA

Expected length  : 15 lines maximum

### Action Line 4 : Face to face training seminars in Geneva :

- 2 seminars

- 15-30 January 98, 7 persons (3 engineers & 4 teachers), 16 days

- 15-30 May 98, 3 persons (1 engineer & 2 teachers), 16 days

- face to face programme as described above Action Line 2

- visits to sites and project-pilots will be organised overall in Switzerland

- evaluation will be made by questionnaires (satisfactory degree of the participants), by direct observation and analyse of the practice (formative evaluation).

To be developed by D Peraya

Responsible : TECFA

Expected length  : 20 lines maximum

### Action Line 5 : Distant follow-up of the face to face seminars

- each period lasts 3 moths and follows each face to face seminar :

- 01.02/30.04.98

- 01.06/30.09.98

- distance education modules using technologies such as Web, Moo, and TUP as described above Action Line 2

- these modules complete and deepen the contents of the face to face seminars

- tutoring through the net and the Internet technologies as described above Action Line 2.

To be developed by D Peraya

Responsible : TECFA

Expected length  : 15 lines maximum

### Action Line 6 : Face to face training seminars in St Petersburg & distant follow-up

- seminars will be organised in the Petersburg Consulting and Training Communication Centre for the teaching and training by the staff trained in Geneva ;

- the Geneva co-ordination team will attempt the first seminar (2 persons, 6 days) for two reasons :

- to assess the « transfer of competencies » and the ability of the members of the staff to play their role in their own context ;

- to help the staff in its role.

To be developed by the CEEC/NIS partners (cf. Your draft, Workplan, item 3 & 4)

For example :

- number and duration of each seminar, target-public, criteria for selection ;

- contents, and programme;

- assessment and certification ;

- estimated number of persons to be trained during the IP programme, and son on..

- follow up

- etc.

Expected length  : 25 lines maximum

### Action Line 7 : Evaluation of the module training in St Petersburg

To be developed by the CEEC/NIS partners. (cf. Your draft, Workplan, last item )

For example :

- description of the evaluation method and tools ;

- in compliance with Action Line 6

Responsible : the CEEC/NIS partners

Expected length  : 15 lines maximum

### Action Line 8 : Evaluation, dissemination and follow-up (15.11/31.12)

- continuing evaluation during the project (regulation process)

- co-responsibility of TECFA and the Centre

- three main steps :

- intermediate report (may, after the first training session)

- final Swiss evaluation mission : the Swiss co-ordination team in St Petersburg : 2 persons, 4 days, end of November : collecting information and data, observation and concertation with the team responsible for the Centre ;

- final report

- dissemination : papers and publication

- after the project : virtual mobility, participation to common forums, research and/or education projects, and so on

To be developed by the CEEC/NIS partners & TECFA

For example :

- how does the Centre work ?

- quality of the infrastructure ?

- number of trained persons

- migration of the Centre’s moo on its own server

- etc.

Co-Responsible : TECFA, the CEEC/NIS partners

Expected length  : 20 lines maximum

## Mobility scheme :

### The face to face seminars in Geneva : illegibility conditions and selected persons

For more details see Action Line 3

#### How many ?

- 12 persons : 6 engineers, 6 teachers and trainers (psychologist, pedagogue), among the engineers will be chosen the Web specialist

- two groups (GR 1 & GR 2) : 8 and 4 persons

- the Web specialist will attempt the two seminars (See Action Line 5)

#### How many time

- 16 days including a face to face seminar in Geneva and visits of sites, and pilot-projects

#### When ?

- 15-30 January 98

- 15-30 May 98

#### Illegibility

To be written by the CEEC/NIS partners. For ; example :

- number of participants from each institution ;

- criteria to be applied for the selection

- etc.

#### List of selected persons

To be written by the CEEC/NIS partners. If possible

### First seminar in St Petersburg

See Action Line 6, (2)

- The Swiss co-ordination team : 2 persons, 6 days

## Shedule

Duration 15 months, 10.01.97 – 12.30.

|  | Oct. | Nov. | Dec. | Jan. |  | Feb. | Mar. | Apr. | May |  | June | Jul. | Aug. | Sept | Oct. | Nov. |  | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AL 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AL 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AL 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Al 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AL5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AL 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AL 7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AL 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Grey background : summer holiday break

Activities of learning organised locally and from a distance by TECFA

Activities organised by the Centre

Mix Activities

# Financial Information

Global Budget : 120.000 CHF

We need to know what amount will be available from own sources of participating CEEC/NIS Institutes (cf D.7 of « Application Forms for IP programme »)

To be written by Pr. Lifshits and Dr T Gavrilova

## Equipment  (D1 of « Application Forms for IP programme »):

Available for the CEEC/NIS partners : up to 36.000 CHF

Equipment and infrastructure have to be strictly described, prices have to be mentioned

To be written by Pr. Lifshits and Dr T Gavrilova

## Mobility (D2 of « Application Forms for IP ¨programme »):

- 1. Seminars in Geneva (2X 6 CEEC/NIS participants, 16 days) :

| Flight (St P-GE-St P) | 12 X 750 CHF | 9.000 CHF |
| --- | --- | --- |
| Board & lodging | 12 X 16 x 150 CHF | 28.800 CHF |
| Travel in CH | 12 X 300 CHF | 3.600 CHF |
| Sub-total 1 |  | 41.400 CHF |

- 2. Co-ordination and evaluation mission in ST Petersburg (2 persons, 7 days)

| Flight (GE-St P-GE) | 2 X 750 CHF | 1.500 CHF |
| --- | --- | --- |
| Board and lodging | 2 X 7 X 150 CHF | 2.100 CHF |
| Sub-total (2) |  | 3.600 CHF |

| Total Mobility Costs | 45.000 CHF |
| --- | --- |

## Subcontracts (D3 of « Application Forms for IP programme »):

Available for TECFA  : up to 9.000 CHF

To be written by TECFA

## Other Costs (D4 of « Application Forms for IP programme »):

General costs (fax, copy), overheads : up to 3.000

## Co-ordination Costs, (D5 of « Application Forms for IP programme »):

(including salary and travel costs for one final evaluation mission)

- 1. Co-ordination in Geneva :

| Co-ordination : class 8.0 (15 months, activity rate 30 % ) : | 24.000 CHF |
| --- | --- |

- 2. Co-ordination and evaluation mission in ST Petersburg (2 persons, 5 days)

| Flight (GE-St P-GE) | 2 X 750 CHF | 1.500 CHF |
| --- | --- | --- |
| Board and lodging | 2 X 5 X 150CHF | 1.500 CHF |
| Sub-total (2) |  | 3.000 CHF |

| Total | 27.000 CHF |
| --- | --- |

# Management and monitoring

This part has to be entirely  written according to the requirements made in the « Instructions for preparation of Global Concept », point 6, Annex 1.2., page 2.

We need inputs and information from our partners, Pr. Lifshits and Dr T Gavrilova. For  instance, we need to know :

- who will become the main correspondent(s) for all the contacts and the management of the project : likely Pr. Lifshits and Dr T Gavrilova, but is that sure ? We need a steering committee including the Swiss co-ordination team and the main CEEC/NIS correspondent.

- how are the CEEC/NIS partners organised : structure, responsibility, internal management ?

- how will the Centre work : structure, organisation, responsibility ?

- how will be the establishment of the infrastructure organised and managed ? (Action Line 1)

- how will the seminars in ST Petersburg be organised : responsibility, selection of participants, from which institution do they come ? (Action Line 6)

- who will be responsible of the evaluation of these seminars (Action Line 7)

Expected length : one page

We, in Tecfa, will describe :

- the general structure of the management : virtual meetings (with a tool like HyperNews), schedule, deliverables and report

- the management of our own Action Lines, and the links between the Action Lines, for example : Action Lines 3, 4 an 5 and Lines 1 and 7.

- the management of the Action Lines in charge of our CEEC/NIS partners according to the received information.

- the general structure of the project : who is responsible of what according to the received information.

- the evaluation process (Action Line 8. ).

# and follow-up

To be written by the partner according to the requirements made in the « Instructions for preparation of Global Concept », point 7, Annex 1.2., page 2.

If the Consortium may be considered as a whole, do not give information for each University, but for the Consortium.

Expected length  : ½  - ¾ page

Concerning the Swiss participation, we may add

The main impact of the IP Programme and the follow up concern collaboration and participation in common programmes. One of the main impact could be the development of monitoring structure at the distance, the starting up of thematic forums and electronic debates between peers in the frame of STAF Courses, exchange of papers, texts, and researches, counselling for dissertations, participation in thesis assessment, and so on. Common publications an dissemination of the experience.

To be developed according to inputs of our partners ;

Information and suggestions needed.